PLANNING TIMELINE

3 MONTHS IN ADVANCE

Choose date and time.

Reserve location if somewhere other than your church.

Decide which format your VBS will be.

Create marketing materials - flyers and social media graphics.

Communicate details to church staff and kidmin volunteers.

Invite some core volunteers who can help you plan an overall picture for VBS to a strategy meeting.

Start feeling out who might want to volunteer at VBS – let them know the dates and times you would need them in advance.

2 MONTHS IN ADVANCE

Invite volunteers to participate.

Print flyers and distribute around church, in mailers, local schools, etc.

Add the event to monthly communications to families.

Order any materials from shopping lists (for both Teaching and Programming).

Begin volunteer trainings and workdays.

6 WEEKS IN ADVANCE

Communicate! Partner with your church to send out additional emails, place bulletin or newsletter announcements, and post social media graphics.

Begin making announcement during your weekly kids' programming.

Continue ordering/confirming materials as needed.

Continue inviting volunteers as needed.

Determine and communicate any technical needs.

Determine and communicate your set-up and tear-down needs for VBS with your team.

4 WEEKS IN ADVANCE

Email volunteers to explain the event outline and answer any questions.

Run background checks for volunteers as needed.

Order any remaining supplies.

Finalize your schedule.

Send email reminder to families.

2 WEEK IN ADVANCE

Send a finalized event schedule and instructions to volunteers.

Finalize volunteer list.

Continue promoting in weekly announcements.

Send out final reminder email to families.

1 WEEK IN ADVANCE

Organize check-in station.

Double-check supply list.

Review all event logistics.

Make final promotional push.

Start setting up decorations.

AFTER THE EVENT

Send thank you notes/emails to all volunteers.

Organize a volunteer appreciation event.

Post a recap video or album of photos on social media.

Follow-up with any new kids/families who attended.

Ask for feedback from families and volunteers on what went well and what could be changed. Make notes for next year!

Formulate an expense report to guide you when you need to set the VBS budget for next year.